## Sheet1
Last Update | Name Of The Program | Description
30 May 2024 | Exploration Drilling Program of “GDH-78/2023” at Pirgonj Upazila of Rangpur District. | <p>GDH-78/23 Drilling completed. Total depth: 3945 ft.( 1202m); Samples have been sent to the ICP-MS and ICP-OES lab for analyses.</p>
07 May 2024 | Coastal Geological and Geomorphological Mapping for the Determination of Terrain Characteristics and Associated Hazards of Phultala and Dumuria Upazilas of Khulna District, Bangladesh | <p>Digitization of data obtained from fieldwork and preparation of maps and reports is in progress.</p>
02 Jul 2024 | Environmental Geology Analysis of Sandwip Upazila and surroundings | <p>The representative samples collected from the field are &nbsp;being &nbsp;analyzed in the various laboratories of GSB.</p>
30 May 2024 | Jamuna River Shifting, Erosion and Deposition Assessment as well as Geological and Geomorphological Mapping of Fulchari Upazila, Gaibandha District | <p>&nbsp;Completed grain size analyses of 16 samples. ; Now preparing a database for litholog construction.</p>
01 Jul 2024 | Geological Mapping of Raozan Upazila of Chattogram District | <p>The Geological map is currently being updated. &nbsp;Granulometric analysis of 10 samples have been completed. Report writting, lithology preparation are on going. &nbsp;</p>
02 Jul 2024 | Engineering Geological Mapping and 3D Modelling for Sustainable Urban Planning in Cumilla City Corporation and Surroundings | <p>Hydrometer tests, sieve analysis, Atterberg limit tests and specific gravity tests conducted on a total of 80, 89, 32 and 80 soil samples, respectively.</p>
01 Jul 2024 | Aquifer delineation and evaluation of sub-surface environment through hydrogeological investigation and preparation of geochemical map of Nawabganj Upazila of Dhaka District | <p>Alkalinity test of 24 water samples have been completed. Cation and trace elements analysis of 28 water samples are being analyzed.&nbsp;</p>
07 May 2024 | Detail Magnetic and Gravity Survey in Parbatipur-Chirirbandar and adjoining areas of Dinajpur District, Bangladesh | <p>Survey completed using Gravity, Magnetic and Land survey instruments. Survey area: 200 sq.km.&nbsp;</p>
01 Jul 2024 | Exploration Drilling Program of “GDH-78/2023” at Pirgonj Upazila of Rangpur District. | <p>Samples have been sent to the ICP-MS and ICP-OES lab for analyses. Preliminary report writing is on progress.&nbsp;</p>
01 Jul 2024 | Research Project: Assessment of the applicability of microgravity survey for the delineation of engineering bedrock - a case study in Aftabnagar, Dhaka | <p>Data processing completed. Data analysis on going for final report preparation.&nbsp;</p>
02 Jul 2024 | Research Project: Characterization of Barind and Madhupur Clay Formations by using Geophysical Techniques. | <p>Field work has already been completed.&nbsp;</p>
01 Jul 2024 | Research Project: Quality assessment of Kaolin Clay of Madhabpur Upazila in Habiganj district and Nalitabari Upazila in Sherpur District for Industrial Potentials | <p>Analytical procedures (Particle size distribution and Plasticity) have been completed for 10 samples.&nbsp;</p>
03 Apr 2024 | Research Project: Recent Changes in coastal erosion in the Cox’s Bazar coast, Bangladesh | To identify the primary factors contributing to the recent significant coastal erosion along the Cox’s Bazar-Teknaf coast and propose potential measures to mitigate erosion, aiming to safeguard Marine Drive Road.
01 Jul 2024 | Research Project: Assessment of Valuable Critical Elements and Geogenic History of Bedload sands of Dharala River in NW Bangladesh | <p>Sample analysis completed. Data &nbsp;analysis on going for final report writing.&nbsp;</p>
14 May 2024 | Spatio-Temporal Morphodynamics Study of Bhola District Using Geo-Spatial Technology as well as Sub-Surface Characterization and Modeling | <p>The field work program is ongoing.&nbsp;</p>